## Overview
Field | Value
Project | Hotel Booking Application - UAT Plan
Version | 1.0
Date | 2025-08-30
UAT Entry Criteria | UAT environment stable; critical defects from SIT resolved; data seeding completed; test accounts created; gateways in sandbox.
UAT Exit Criteria | All High-priority tests passed; Medium with acceptable workarounds documented; no Critical/Blocker defects open; stakeholders sign-off.
Scope | Public booking site, PMS (front desk, housekeeping, maintenance), payments, reporting, admin, integrations.
Out of Scope | Penetration testing, load testing at production scale (covered in performance testing).
Stakeholders | Product Owner, Hotel Ops Lead, Finance, QA Lead, Engineering, Support.

## TestCases
ID | Module | Title | Pre-Conditions | Test Data | Steps | Expected Result | Acceptance Criteria | Priority | Type | Environment | Owner | Evidence (Link/File) | Status (Pass/Fail/Blocked/NA)
AUTH-001 | Authentication | Sign up with email & strong password | No existing account for test email. | Email: guest1@example.com; Password: P@ssw0rd!234 | 1. Open /signup 2. Enter email & password 3. Accept terms 4. Submit 5. Verify email via link | Account is created. Verification email received. After verification, login succeeds and lands on dashboard. | Email must be unique; password policy enforced; verification completes within 2 minutes; user redirected to dashboard on first login. | High | Happy Path | UAT | Business Tester
AUTH-002 | Authentication | Login with valid credentials | User account exists & verified. | Email: guest1@example.com; Password: P@ssw0rd!234 | 1. Open /login 2. Enter credentials 3. Click Login | User is authenticated and taken to Home; session cookie/JWT created. | Auth token issued; session persists across navigation; logout clears session. | High | Happy Path | UAT | Business Tester
AUTH-003 | Authentication | Rate-limit on failed logins | User account exists. | Email: guest1@example.com; Invalid password | 1. Attempt login with wrong password 6 times within 5 min | User sees friendly error messages. After threshold, further attempts are blocked for 15 minutes; audit entry created. | Lockout threshold and duration match config; no PII leaked in error text. | Medium | Negative | UAT | Business Tester
TEN-001 | Multi-Tenant | Create hotel (tenant) with basic profile | Platform Admin logged in. | Hotel Name: 'Sunrise Addis Hotel'; Timezone: Africa/Addis_Ababa; Currency: ETB; Locale: en-ET | 1. Navigate: Platform → Hotels → New 2. Fill profile & contacts 3. Save | Tenant created; unique tenant ID and subdomain generated (e.g., sunrise.addis.example.com). | All required fields validated; duplicate names prevented; audit trail captured. | High | Happy Path | UAT | Business Tester
TEN-002 | Multi-Tenant | Tenant user roles & permissions | Tenant exists. Users created for TENANTADMIN, FRONTDESKSTAFF, HOUSEKEEPINGSTAFF, MAINTENANCESTAFF. | Users with roles above | 1. Login as TENANTADMIN → can access Setup & Reports 2. Login as FRONTDESKSTAFF → cannot access Setup; can create booking 3. Login as HOUSEKEEPINGSTAFF → access only Rooms/Tasks 4. Login as MAINTENANCESTAFF → access Maintenance tickets only | RBAC enforced per role; unauthorized areas hidden and blocked by API. | Least-privilege enforced; authorization checked server-side; attempts logged. | High | Happy Path | UAT | Business Tester
INV-001 | Inventory | Create room types & rooms | Tenant admin logged in. | Room Types: Deluxe King, Standard Twin; Rooms: 101–110 (Deluxe), 201–220 (Twin) | 1. Setup → Rooms → Add Room Type (Deluxe King) 2. Add attributes (bed type, max guests, amenities) 3. Bulk-create rooms 101–110 4. Repeat for Standard Twin 201–220 | Room types & rooms appear in inventory with correct capacity and amenities; room count totals correct. | Rooms uniquely identified; capacity & amenities saved; bulk creation error-handles duplicates. | High | Happy Path | UAT | Business Tester
RATE-001 | Rates | Create base BAR and non-refundable rate plans | Room types exist. | Rate Plans: BAR (cancellable 24h), NR (non-refundable -10%) | 1. Setup → Rates → New → BAR 2. Set policies & cancellation 3. Clone to create NR with -10% adjustment | Both plans visible and bookable with correct rules. | Derived pricing calculates correctly; policies show on checkout & emails. | High | Happy Path | UAT | Business Tester
AV-001 | Availability | Load availability calendar and close outs | Rooms and rates exist. | Close-out: Deluxe King for 2025-12-01; Min Stay: 2 nights on 2025-12-24 | 1. Setup → Availability → Calendar 2. Apply close-out and min-stay rules 3. Save 4. Search for those dates | Closed-out rooms not returned; min-stay enforced in search/checkout. | Search respects inventory rules; UI badges reflect constraints. | High | Happy Path | UAT | Business Tester
SRCH-001 | Search | Basic search returns available rooms | Availability loaded; no close-out for selected dates. | Check-in 2025-10-10; 2 nights; 2 adults | 1. Open public booking site 2. Enter dates & guests 3. Search | Results show available room types with correct prices per night and total. | Currency & tax displayed; pagination/filters work; performance < 2s. | High | Happy Path | UAT | Business Tester
BOOK-001 | Booking | Happy path booking with card (Stripe) | Payment gateway sandbox keys configured. | Guest: John Doe; Email: john@example.com; Visa test 4242 4242 4242 4242; Check-in 2025-10-10 (2 nights) | 1. Select room → Choose BAR 2. Enter guest details 3. Enter card & billing address 4. Confirm & pay | Booking is confirmed; reservation number generated; confirmation page + email sent to guest and hotel. | Payment authorized; folio shows room, taxes, fees; email contains correct details & terms. | High | Happy Path | UAT | Business Tester
BOOK-002 | Booking | 3‑D Secure challenge (SCA) | Gateway supports 3DS in sandbox. | Use 3DS required test card | 1. Repeat BOOK-001 with 3DS test card 2. Complete challenge frame | Payment succeeds after 3DS; booking confirmed. | Challenge iframe renders; fallback if user cancels challenge. | High | Edge | UAT | Business Tester
BOOK-003 | Booking | Booking with promotional code | Promo code 'WELCOME10' active for BAR, 10% off, min spend $100. | Promo: WELCOME10 | 1. Search eligible dates 2. Apply promo on checkout | Discount applied to nightly rate; terms displayed; cannot combine with NR. | Promo validation server-side; misuse blocked; audit logged. | High | Happy Path | UAT | Business Tester
BOOK-004 | Booking | Booking holds inventory to prevent overbooking | Only 1 Deluxe room left for 2025-10-10 to 2025-10-12. | Two concurrent users A and B | 1. A and B select same room & dates 2. A completes payment first 3. B attempts to pay | B is prevented from double-selling; receives 'no longer available' message and advised to select alternatives. | Atomic inventory hold & release; consistent across tabs/devices. | High | Concurrency | UAT | Business Tester
BOOK-005 | Booking | Booking with wallet/mobile money (ETB) | ETB wallet provider sandbox configured. | Phone: +251-900-000000 | 1. Select rate in ETB 2. Choose wallet method 3. Approve on phone 4. Return to success page | Payment captured; booking confirmed; receipt reflects ETB and exchange if applicable. | Callback handled once; idempotent booking creation. | High | Happy Path | UAT | Business Tester
MOD-001 | Changes | Modify dates within policy | Existing BAR booking for 2025-10-10 (2 nights). | Change to 2025-10-12 (2 nights) | 1. Open 'Manage Booking' with confirmation & email 2. Edit dates 3. Accept fare difference 4. Confirm | Booking updated; new confirmation sent; payment difference charged/refunded accordingly. | Rules enforced; original confirmation number retained or linked; audit trail kept. | High | Happy Path | UAT | Business Tester
CXL-001 | Cancellation | Cancel within free window | BAR booking with 24h free cancellation. | — | 1. Manage Booking → Cancel 2. Confirm cancellation | Status changes to Cancelled; email sent; full refund initiated. | Refund transaction posted; ledger shows offset entry. | High | Happy Path | UAT | Business Tester
CXL-002 | Cancellation | Attempt cancel NR (non-refundable) | NR booking exists. | — | 1. Manage Booking → Cancel | System blocks cancellation or offers voucher per policy. | Clear message with policy terms; no refund transaction created. | High | Negative | UAT | Business Tester
FD-001 | Front Desk | Walk-in booking at PMS | Front desk logged in; inventory available. | Guest details; cash payment | 1. PMS → Create Reservation 2. Assign room 101 3. Take cash deposit 4. Print registration card | Reservation created; folio shows cash transaction; room 101 blocked. | Printed docs include terms; cashier shift tally updated. | High | Happy Path | UAT | Business Tester
FD-002 | Front Desk | Check-in & key issue | Guest has confirmed booking for today; room clean. | ID: Passport 12345 | 1. Open reservation → Check-in 2. Capture ID & signature 3. Issue key (encode or digital key) | Status = In-House; key active; housekeeping status 'Occupied'. | Timestamp recorded; key deactivates at checkout. | High | Happy Path | UAT | Business Tester
HK-001 | Housekeeping | Room status workflow (Dirty → Clean) | Housekeeping user logged in; checkout completed for room 201. | — | 1. HK app lists 'Dirty' rooms 2. Start task for 201 3. Mark 'Clean' with notes/photos | Room 201 becomes 'Clean'; available for assignment. | Timestamps & user recorded; photos stored; SLA met. | High | Happy Path | UAT | Business Tester
MAIN-001 | Maintenance | Create & resolve maintenance ticket | Room 110 reported AC issue. | Issue: AC not cooling; Priority: High | 1. Front desk creates ticket & tags room 110 2. Maintenance accepts & resolves 3. Close ticket | Ticket lifecycle tracked; room status 'OOO' (out of order) during repair; returned to 'Clean' when done. | OOO blocks booking; reports show downtime. | High | Happy Path | UAT | Business Tester
BILL-001 | Billing | Split folio items on checkout | Guest in-house with room + minibar charges. | Split room to Company A, incidentals to Guest card | 1. Open folio → Split by payer 2. Assign charges 3. Close folios 4. Email invoices | Two invoices generated to respective payers; totals reconcile; payment captured as per allocation. | Tax totals accurate; PDFs render correctly. | High | Happy Path | UAT | Business Tester
BILL-002 | Billing | Tax/VAT calculation by locale | Hotel configured with 15% VAT (ET). | Room rate 1,000 ETB/night x2 nights | 1. Create booking 2. Review folio taxes | VAT computed at 15% on eligible items; tax ID shown on invoice. | Rounding rules per config; exemptions handled when flagged. | High | Happy Path | UAT | Business Tester
RPT-001 | Reporting | Daily arrivals & housekeeping reports | Existing bookings for today. | — | 1. Reports → Arrivals 2. Reports → HK Schedule | Arrivals list matches reservations; HK report shows room status & tasks. | Totals align with dashboard; export to CSV/PDF works. | High | Happy Path | UAT | Business Tester
COMM-001 | Communications | Email templates render correctly | SMTP configured; templates for confirmation, modification, cancellation. | — | 1. Trigger each email 2. Inspect subject, sender, reply-to, body, variables | Dynamic fields (guest name, dates, hotel name) populate; DKIM/SPF alignment passes; links work. | No PII leakage; unsubscribe for marketing emails only. | High | Happy Path | UAT | Business Tester
COMM-002 | Communications | SMS confirmation (optional) | SMS gateway sandbox configured. | Phone: +1 555-000-1111 | 1. Opt-in SMS at checkout 2. Complete booking | Confirmation SMS received with short URL to manage booking. | Consent recorded; STOP/HELP keywords supported. | High | Happy Path | UAT | Business Tester
OTA-001 | Integrations | Availability sync to channel manager | Channel manager sandbox connected. | — | 1. Change inventory (close-out 101) 2. Push sync | External channels reflect change within SLA; no errors. | Sync logs show success; retries on failure. | High | Happy Path | UAT | Business Tester
OTA-002 | Integrations | Reservation import from OTA | OTA booking exists in sandbox. | — | 1. Receive reservation push 2. Verify PMS | Reservation appears with correct mapping, payment tokenization, and source marked as OTA. | No duplicate creation; rate/room mapping correct. | High | Happy Path | UAT | Business Tester
LOY-001 | Loyalty | Enroll guest & earn points | Loyalty program enabled. | Guest: john@example.com; Earn rate: 10 pts per $1 | 1. Enroll guest 2. Complete $200 stay 3. Post-stay run points job | 2,000 points added; balance visible in account. | Points accrual matches rules; rounding as specified. | High | Happy Path | UAT | Business Tester
LOY-002 | Loyalty | Redeem points for free night | Guest has 20,000 points; redemption rule 20k/night. | — | 1. Search eligible dates 2. Apply points at checkout | Price reduces to 0 room rate; taxes/fees per policy remain. | Ledger reflects points deduction; booking notes show redemption. | High | Happy Path | UAT | Business Tester
SEC-001 | Security | PII masking in logs & exports | System logging at INFO. | — | 1. Make a booking 2. Review logs & exports | No full card numbers or sensitive PII in logs; exports require permission. | Compliance with PCI-DSS scope; access attempts audited. | High | Compliance | UAT | Business Tester
SEC-002 | Security | Session timeout & logout | User logged in. | Timeout set to 15 min idle | 1. Idle for 15+ min 2. Try protected page 3. Login again | User is logged out and redirected to login; unsaved changes warning appears where relevant. | No access with expired token; refresh tokens invalidated on logout. | Medium | Happy Path | UAT | Business Tester
LOC-001 | Localization | Currency/locale switching | Locales enabled: en-US, am-ET; Currencies: USD, ETB. | — | 1. Switch to am-ET & ETB 2. Search & book | Dates, numbers, and text localize; pricing uses correct currency symbol and formatting. | RTL/UTF-8 rendering OK; no layout breaks. | High | Happy Path | UAT | Business Tester
A11Y-001 | Accessibility | Keyboard navigation & screen-reader labels | Public site accessible. | — | 1. Navigate with keyboard only 2. Inspect aria-labels 3. Use screen reader | All interactive elements reachable; proper focus order; labels announced correctly. | Meets WCAG 2.1 AA for tested pages. | Medium | Non-Functional | UAT | Business Tester
PERF-001 | Performance | Search results response time | Environment stable; baseline captured. | — | 1. Perform search at peak test window (N=20) 2. Measure TTFB | P95 < 2s; no errors. | Meets agreed UAT NFR threshold. | Medium | Non-Functional | UAT | Business Tester
PERF-002 | Performance | Checkout throughput (light load) | Gateway sandbox; no external throttling. | — | 1. Execute 10 sequential bookings 2. Capture success rate and mean duration | Success ≥ 99%; mean < 10s per booking. | No leak of reserved inventory on failure. | Medium | Non-Functional | UAT | Business Tester
MIG-001 | Data | Import legacy rates & rooms | CSV import tool configured. | CSV with 2 room types, 30 rooms | 1. Upload CSV 2. Validate preview 3. Import | Inventory created; bad rows reported with reasons. | Row counts match; no partial silent failures. | High | Happy Path | UAT | Business Tester
MIG-002 | Data | Reconciliation report accuracy | Bookings exist across sources. | — | 1. Run daily revenue report 2. Cross-check with sample bookings | Totals match folio sums; OTA vs Direct split accurate. | ±0 tolerance for sample set; rounding rules documented. | High | Happy Path | UAT | Business Tester
MOB-001 | Mobile | Responsive booking flow (iOS/Android) | Use iPhone 13 Pro (Safari) & Pixel 6 (Chrome). | — | 1. Repeat BOOK-001 on mobile devices 2. Validate tap targets & virtual keyboard types | No layout overflow; numeric keypad for numbers; sticky CTA visible. | Core Web Vitals within acceptable ranges on UAT. | Medium | Happy Path | UAT | Business Tester
BR-001 | Browser | Supported browsers matrix | Supported: Chrome, Safari, Firefox, Edge (last 2 versions). | — | 1. Smoke test journey on each browser | Key flows work across browsers; no console errors blocking actions. | Polyfills loaded where needed. | Low | Happy Path | UAT | Business Tester
NEG-001 | Validation | Invalid guest counts vs room capacity | Room capacity 2. | Guests: 3 adults | 1. Search with 3 adults for room cap 2 | System prevents selection or suggests suitable rooms. | Server-side validation blocks checkout with clear message. | High | Negative | UAT | Business Tester
NEG-002 | Validation | Expired promo code | Promo WELCOME10 expired yesterday. | WELCOME10 | 1. Apply code on checkout | Code rejected with reason; pricing unchanged. | Attempt logged; UI accessible to enter new code. | High | Negative | UAT | Business Tester
NEG-003 | Payments | Card decline handling | Use gateway decline code card_declined. | Decline test card | 1. Enter card and submit | Clear error shown; no booking created; inventory released promptly. | No duplicate charges; retry allowed. | High | Negative | UAT | Business Tester
NEG-004 | Concurrency | Double-click pay button | Checkout page ready. | — | 1. Double-click Pay quickly | Only one payment/booking created; others ignored as duplicates. | Idempotency key enforced. | High | Edge | UAT | Business Tester
ADM-001 | Admin | Change logs & audit trail | Tenant admin exists. | — | 1. Update rate plan 2. Change room amenity 3. Review audit log | Each change recorded with who/when/what before & after. | Export works; time zone consistent. | High | Happy Path | UAT | Business Tester
ADM-002 | Admin | GDPR/CCPA data request (export & delete) | Guest has past bookings. | Email: privacy.request@example.com | 1. Submit data export request 2. Verify export package 3. Submit delete request (where allowed) | Export contains user data; deletion anonymizes PII while keeping financial records as required. | SLA met; notifications sent to requester. | High | Compliance | UAT | Business Tester

## NonFunctional
Area | Scenario | How to Validate | Acceptance
Performance | Search P95 < 2s | Run 50 manual searches during UAT window; capture timestamps. | 95th percentile < 2s
Reliability | No data loss on payment failure | Inject gateway declines; verify inventory release. | Zero stuck holds
Security | AuthZ checks on APIs | Attempt unauthorized endpoints with lower role. | 403 with no data leakage
A11y | WCAG 2.1 AA basics | Keyboard-only + screen reader pass. | Critical paths usable
Localization | am-ET & ETB | Prices and dates localized. | Correct symbols/formatting
Backup/DR | Daily DB snapshot | Verify snapshot presence & restore plan doc. | Snapshots visible for last 7 days

## Traceability
Business Requirement ID | Description | Covered By
BR-01 | Guests can book rooms online with card payment. | ['BOOK-001', 'BOOK-002', 'NEG-003', 'NEG-004']
BR-02 | Hotel staff manage check-in/out and housekeeping. | ['FD-002', 'HK-001', 'BILL-001']
BR-03 | System supports promotions and loyalty. | ['BOOK-003', 'LOY-001', 'LOY-002', 'NEG-002']
BR-04 | Multi-tenant isolation with RBAC. | ['TEN-002', 'SEC-001', 'SEC-002', 'ADM-001']

## DefectsLog
Defect ID | Reported By | Date | Linked Test ID | Module | Severity (Critical/High/Medium/Low) | Summary | Steps to Reproduce | Expected | Actual | Attachments | Status | Owner | ETA